KENYATTA UNIVERSITY  |  CENTRE FOR DESIGN, INNOVATION AND ENTREPRENEURSHIP (CDIE)  |  INVENTION EDUCATION (IvE) PROGRAMME

BactoAI: Validating a Genomic AMR Prediction Model

Review of the draft letter to NPHL/KNPHI, recommended training and testing datasets, and guiding questions for the BactoAI team

| Item | Detail |
| --- | --- |
| Venture | BactoAI – machine-learning prediction of antimicrobial resistance (AMR) from bacterial whole-genome sequencing (WGS) data |
| Team lead | Mr. Samwel Azivirwa Elegwa, Founder and CEO (final-year BSc Biotechnology) |
| Document reviewed | Draft letter of support dated 18 October 2026, addressed to the Director, National Public Health Laboratory (NPHL) / Kenya National Public Health Institute (KNPHI) |
| Prepared by | Dr. Kenneth Malongo Iloka, Co-PI, MDI and IvE Programmes, Kenyatta University |
| Date | 26 October 2026 |
| Action required | Read Sections 1–4. Answer the guiding questions in Section 5 and return them with the deliverables in Section 6. Use your answers to complete the revised letter in Annex A before it is signed and sent. |

# Purpose

BactoAI’s draft letter asks NPHL/KNPHI to support external validation of its models, a data partnership, and a pathway towards clinical evaluation. As a national reference laboratory, NPHL reviewers will first look at the evidence behind the performance figures quoted in the letter. Before Kenyatta University signs the letter, the team must back each claim with documented evidence it can present if asked.

This note therefore does four things: it reviews the letter claim by claim (Section 2); lists public datasets the team can use for training and, separately, for independent testing (Section 3); sets out the validation procedure to follow before and during work with NPHL (Section 4); and poses guiding questions mapped to each claim (Section 5). Annex A gives suggested revised wording for the letter, with placeholders to be filled from your answers.

# Review of the draft letter

## Overall assessment

The letter is clear, well structured and appropriately modest: it states that results are retrospective, that independent confirmation is needed, and that the tool supports rather than replaces culture. Its commitments to ethical review, the Data Protection Act, 2019, and sharing findings are exactly what NPHL will expect. The main gap is that the performance claims are stated without the information a reference laboratory needs to judge them. The items below should be resolved before signature.

## Claim-by-claim review

| Statement in the letter | Concern | What the team must provide or change | Questions |
| --- | --- | --- | --- |
| “predict resistance … in under ten minutes, whereas conventional culture-based testing takes days” | WGS itself requires a cultured isolate, DNA extraction and sequencing, which take one to several days. Comparing model run-time with the whole culture workflow may be read as overstated. | State the starting point of the ten minutes (e.g., from an assembled genome) and the realistic end-to-end turnaround. Describe the advantage accurately: faster, broader resistance profiling once a genome exists. | Q2–Q3 |
| “trained on more than 1,800 clinical isolates” | Species, data sources, countries and AST methods are not stated. If few or no isolates are Kenyan, performance on local strains is unknown. | Give counts per species and per antibiotic, the sources (NCBI resources used), countries and years, and the number of African/Kenyan isolates. | Q1, Q5–Q9 |
| “Meropenem model achieved a ROC-AUC of 0.952, and the Ciprofloxacin and Cefotaxime models 0.872” | ROC-AUC alone does not show clinical usefulness. The test design (random vs. relatedness-aware split) is not stated, and random splits tend to inflate results. Two different drugs reporting the identical value is possible but unusual and should be checked. | Confirm each value separately. Report test-set size, how it was split, sensitivity, specificity, very major and major error rates, and 95% confidence intervals per drug, plus a comparison with a rule-based tool. | Q18–Q26 |
| “its results to date come from retrospective data” | Accurate, but NPHL will want to know whether any testing has been done on data from a source independent of training. | Run at least one external test on an independent public dataset (Section 3.2) before approaching NPHL, and report it in the letter or technical summary. | Q27–Q28 |
| “consider a data partnership … so that the models can be retrained” | If NPHL data are used both to retrain and to validate, the validation is no longer independent. | Commit to holding back a locked portion of NPHL data, never used in training, for validation. Freeze the model version before validation begins. | Q30–Q31 |
| “a pathway towards clinical trials” | For a diagnostic tool the usual next step is a diagnostic accuracy or clinical performance study, not a trial. Software used to inform diagnosis may also fall under medical device regulation. | Reframe as a prospective clinical performance evaluation following STARD. Identify the regulatory route with the Pharmacy and Poisons Board and draft an intended-use statement. | Q35 |
| “deployed a working prototype, with a live web platform and a hosted model backend” | If NPHL genomic data are uploaded, hosting location, security and cross-border transfer matter under the Data Protection Act, 2019. | State where the platform is hosted, how data are secured and deleted, and whether the team is registered with the Office of the Data Protection Commissioner. | Q32–Q33 |
| Requests: validation, clinical pathway, data partnership, incubation and mentorship | Four asks in one paragraph dilute the main request. | List them in priority order, with external validation first. Propose an introductory meeting and attach a two-page technical summary. | – |
| Signature block “[Name, title and signature]” | Incomplete; no letterhead or reference number. | Print on KU letterhead with a reference number and the name and title of the signatory. Enclose the technical summary. | – |

# Recommended data sources

BactoAI’s models target gram-negative bacteria and three antibiotics: meropenem (carbapenem), ciprofloxacin (fluoroquinolone) and cefotaxime (third-generation cephalosporin). The sources below provide genomes paired with laboratory susceptibility results (S/I/R calls or MICs) for these organisms. Check which of the three drugs each source covers before use.

## Training sources (likely already used)

| Source | Organisms | What it provides | Access and cautions |
| --- | --- | --- | --- |
| NCBI Pathogen Detection – AST Browser ncbi.nlm.nih.gov/pathogens/ast | E. coli, Klebsiella, Salmonella, Acinetobacter, Pseudomonas and others | Submitted AST data (MIC and disk diffusion) linked to isolate genomes and AMRFinderPlus gene calls. | NCBI does not vet AST methods or values beyond basic quality control. Filter by testing standard (CLSI/EUCAST), method and year. MIC and disk-diffusion data are in separate columns. |
| NCBI Isolates Browser and MicroBIGG-E ncbi.nlm.nih.gov/pathogens/isolates ncbi.nlm.nih.gov/pathogens/microbigge | As above | Isolate metadata (country, host, source, date, SNP cluster) and detected resistance genes and point mutations (e.g., carbapenemases, CTX-M, gyrA/parC). | Use SNP-cluster IDs to keep related isolates in the same split (Section 4). |
| NCBI BioSample (antibiogram filter) BioSample: antibiogram[filter] | All bacteria with submitted antibiograms | BioSample records that carry an antibiogram table; links to SRA reads and assemblies. | Use BioSample accessions to de-duplicate across databases. |
| BV-BRC (formerly PATRIC) – AMR phenotypes bv-brc.org Bulk file: ftp.bvbrc.org/RELEASE_NOTES/PATRIC_genomes_AMR.txt | Wide range, incl. A. baumannii, K. pneumoniae, P. aeruginosa, E. coli | Curated genome–AST pairs from published studies, with MIC, method and source fields. | Exclude rows marked “Computational Prediction”. Overlaps heavily with NCBI; de-duplicate by BioSample. |

## Independent testing and external validation sources

A test set is independent only if no isolate in it, or a near-identical clone, was used in training. Check every candidate set against the master isolate table by BioSample and SRA accession before use. If a dataset below was part of the 1,800+ training isolates, it cannot serve as an external test set.

| Source | Organisms | What it provides | Access and cautions |
| --- | --- | --- | --- |
| Liverpool E. coli WGS–AST dataset datacat.liverpool.ac.uk/3008 | Escherichia coli | 762 clinical isolates with WGS and AST metadata, chosen to represent important resistance mechanisms; built for ML prediction of MIC. | Recent (2025) and likely independent of NCBI-derived training data. Confirm drug coverage and accession overlap. |
| Moradigaravand et al. (2018) E. coli collection doi:10.1371/journal.pcbi.1006258 | Escherichia coli | About 1,900 UK bloodstream isolates with genomes and AST to multiple antibiotics, used for pan-genome-based ML prediction. | Widely used in AMR ML work. Check first whether it is already in the training set. |
| Nguyen et al. (2018) K. pneumoniae MIC set doi:10.1038/s41598-017-18972-w | Klebsiella pneumoniae | About 1,600 isolates with genomes and MICs for 20 antibiotics, used to build an in-silico MIC panel. | Useful for carbapenem and cephalosporin resistance in Klebsiella. Data are available via BV-BRC; check overlap. |
| Hu et al. (2024) AMR benchmark doi:10.1093/bib/bbae206 | Multiple species–antibiotic combinations | Curated benchmark datasets, evaluation guidelines and metrics for rule-based and ML prediction of AMR phenotypes. | Allows direct comparison with published tools on the same splits. |
| Kenyan / East African public isolates NCBI Isolates Browser European Nucleotide Archive | Gram-negative species of the study | Isolates with geo_loc_name = Kenya (or neighbouring countries) and AST data, plus published East African studies that deposited reads. | Hold out completely from training. Gives a first indication of local performance before NPHL data are available. |
| NPHL/KNPHI isolates (requested partnership) | Gram-negative clinical isolates | Locally sequenced isolates with reference phenotypic AST, under NPHL protocols. | The definitive external validation set. Keep a locked validation portion separate from any retraining data. |

Note: the CRyPTIC dataset discussed earlier covers only M. tuberculosis and is not relevant to BactoAI’s current gram-negative models.

## Reference tools for a rule-based baseline

| Tool / database | Link | Use |
| --- | --- | --- |
| AMRFinderPlus and NCBI Reference Gene Catalog | ncbi.nlm.nih.gov/pathogens/antimicrobial-resistance/AMRFinder | Detects acquired genes (e.g., carbapenemases, ESBLs) and point mutations (e.g., gyrA, parC). |
| CARD / Resistance Gene Identifier | card.mcmaster.ca | Curated resistance ontology and gene identification. |
| ResFinder / PointFinder | genepi.food.dtu.dk/resfinder | Gene- and mutation-based phenotype prediction for many species. |
| EUCAST / CLSI breakpoints | eucast.org/clinical_breakpoints clsi.org (M100) | Re-interpret MICs into S/I/R consistently across sources. |

# Validation procedure

Validation should happen in two stages. Stage 1 can be completed now with public data and will strengthen the letter. Stage 2 is the work requested from NPHL.

## Stage 1 – Retrospective validation on public data (before the letter is sent)

- Define the prediction task. State the species and antibiotics each model covers, and whether output is S/R, S/I/R or MIC.

- Record data provenance. Build a master isolate table: BioSample, SRA/assembly accession, source database, country, year, AST method, standard and breakpoint version.

- Harmonise labels. Re-interpret MICs with one breakpoint standard and version; set one rule for intermediate results; remove computationally predicted phenotypes.

- Quality-control genomes. Apply thresholds for contamination, completeness, contig count and genome size; confirm species.

- De-duplicate across sources. Match isolates by BioSample so none appears in both training and testing.

- Split by relatedness. Keep isolates from the same SNP cluster, sequence type or clade within one split. Re-compute the reported ROC-AUC figures under this design.

- Test on an independent dataset. Score at least one external set from Section 3.2 and, if available, Kenyan public isolates.

- Compare with a rule-based baseline. Score the same isolates with AMRFinderPlus or ResFinder.

- Report full metrics. Per drug: sensitivity, specificity, balanced accuracy, AUROC, AUPRC, very major error rate (resistant called susceptible), major error rate (susceptible called resistant), with 95% confidence intervals.

## Stage 2 – External validation with NPHL (requested in the letter)

- Freeze the model. Lock and record the model version, code and thresholds before any NPHL data are scored.

- Agree a written protocol with NPHL. Specify species, antibiotics, sample size, the reference AST method (e.g., broth microdilution per ISO 20776-1, interpreted with CLSI or EUCAST), and blinding of laboratory staff to predictions.

- Obtain approvals. Ethical approval from an accredited research ethics committee and a NACOSTI research licence; data-sharing agreement; data protection impact assessment.

- Separate validation from retraining data. Set aside a locked validation portion of NPHL data that is never used for training or tuning.

- Analyse and report. Report categorical agreement, very major and major errors (as used in ISO 20776-2 evaluations), and follow the STARD and TRIPOD+AI reporting guidelines. Share results with NPHL.

# Guiding questions for the BactoAI team

Answer each question specifically. Give numbers, accessions or file references where asked. Write “not yet done” where that is the honest answer. The “Letter link” column shows which statement in the letter each answer supports.

## The product and the claims in the letter

| No. | Question | Letter link | Team response |
| --- | --- | --- | --- |
| 1 | Which bacterial species do the meropenem, ciprofloxacin and cefotaxime models cover? Is there one model per drug across species, or one per species–drug pair? | Gram-negative focus | One model per antibiotic (cross-species), not per species-drug pair. Species included: - Meropenem: A. baumannii (98), K. pneumoniae (152), E. coli/Shigella (198), P. aeruginosa (63), S. enterica (87), E. cloacae (2) = 600 isolates - Ciprofloxacin: E. coli/Shigella (287), S. enterica (133), A. baumannii (86), K. pneumoniae (54), P. aeruginosa (39), E. cloacae (1) = 600 isolates - Cefotaxime v4: E. coli/Shigella (222 NCBI + 3,419 BV-BRC), K. pneumoniae (219), A. baumannii (114), S. enterica (43), P. aeruginosa (1), E. cloacae (1) = 4,019 isolates See: data/metadata_*.csv, bactoai_pipeline.py, BVBRC_INTEGRATION_AND_VALIDATION_REPORT.md |
| 2 | What does the “under ten minutes” start from (raw reads, assembled genome) and what does it include? What is the realistic total time from patient sample to result? | Ten-minute claim | 'Under ten minutes' = computational prediction time from assembled genome (FASTA) to resistance call. Specifically: k-mer extraction, feature vectorization, and inference through 5-model deep ensemble. Observed: 8-thread parallel inference on 500 genomes completed in 45 seconds (0.09s/genome). Single genome prediction: <1 second. Realistic total sample-to-result: 1. Culture/isolation: 1-2 days 2. DNA extraction: 2-4 hours 3. WGS (Illumina): 12-36 hours; (Nanopore MinION): 2-8 hours 4. Assembly: 30 min - 2 hours 5. BactoAI prediction: <1 minute Total: ~2-4 days (vs 3-5 days for conventional phenotypic AST). See: bactoai_pipeline.py (predict_genome function timing), README.md |
| 3 | What sequencing platform and file types does the tool accept (e.g., Illumina or Nanopore; FASTQ or FASTA)? Does this match what NPHL produces? | Ten-minute claim | Accepts: FASTA (.fna, .fasta), including gzip-compressed (.fna.gz). Input: assembled contigs (not raw reads). Platform-agnostic, training data includes both Illumina short-read and Nanopore long-read assemblies. NPHL compatibility: NPHL uses Illumina MiSeq and NextSeq, producing assembled genomes in FASTA format. Fully compatible. See: bactoai_pipeline.py read_fasta(), templates/index.html |
| 4 | Are there models for other antibiotics? Why were these three highlighted in the letter? | Performance claims | Currently deployed: meropenem, ciprofloxacin, cefotaxime only. These three were selected for clinical priority in Kenya/East Africa: - Meropenem: last-line carbapenem; carbapenem resistance = WHO Priority 1 Critical threat - Ciprofloxacin: first-line for many Gram-negatives; resistance >60% in LMIC hospitals - Cefotaxime: widely used empiric therapy; ESBL-mediated resistance expanding rapidly Roadmap includes expansion to: ceftriaxone, ceftazidime, gentamicin, amikacin, colistin. See: DATASET_ORGANISMS_AND_AMR_ACQUISITION_STRATEGY.md, ROADMAP.md |

## Training data (the 1,800+ clinical isolates)

| No. | Question | Letter link | Team response |
| --- | --- | --- | --- |
| 5 | Which NCBI resources did you use (AST Browser, Isolates Browser, BioSample, SRA, GenBank)? Give search terms, filters and download date. | 1,800+ isolates | Sources: 1. NCBI Pathogen Detection AST Browser (ncbi.nlm.nih.gov/pathogens/ast), primary source, 600 isolates/drug 2. NCBI Isolates Browser (ncbi.nlm.nih.gov/pathogens/isolates), metadata, SNP clusters, country 3. NCBI SRA and GenBank, genome assemblies via accession (GCA_* in metadata CSVs) 4. Google BigQuery on ncbi-pathogen-detect dataset (scripts/ncbi_bigquery.py), geographic priors Filters: target antibiotics (meropenem, ciprofloxacin, cefotaxime), Gram-negative pathogens (taxon IDs for E. coli, K. pneumoniae, A. baumannii, P. aeruginosa, S. enterica), S/I/R phenotype labels. Download dates: NCBI batch mid-2026 (pipeline header: Created 2026-07-22); BV-BRC batch September 2026. See: scripts/ncbi_bigquery.py, data/metadata_*.csv |
| 6 | How many isolates were downloaded, and how many remained after cleaning? Give counts per species, per antibiotic and per S/I/R class. | 1,800+ isolates | Per antibiotic (NCBI batch, post-cleaning): ¦ Drug ¦ Downloaded ¦ After cleaning ¦ Resistant ¦ Susceptible ¦ ¦---¦---¦---¦---¦---¦ ¦ Meropenem ¦ ~600 ¦ 600 ¦ 300 ¦ 300 ¦ ¦ Ciprofloxacin ¦ ~600 ¦ 600 ¦ 300 ¦ 300 ¦ ¦ Cefotaxime (NCBI v3) ¦ ~600 ¦ 600 ¦ 300 ¦ 300 ¦ ¦ Cefotaxime (BV-BRC) ¦ 6,260 raw ¦ 3,419 after cleaning ¦ 384 ¦ 3,035 ¦ ¦ Cefotaxime (combined v4) ¦ -- ¦ 4019 ¦ 684 ¦ 3335 ¦ Total unique isolates: ~1,800 NCBI + 3,419 BV-BRC = ~5,219 (with NCBI cefotaxime counted once). The '1,800+' claim refers to the NCBI batch. With BV-BRC integration, total exceeds 5,200. See: data/training_summary_v3.csv, data/training_summary_v4.csv, BVBRC_INTEGRATION_AND_VALIDATION_REPORT.md |
| 7 | Which countries, years and settings are represented? How many isolates are African, and how many Kenyan? | Local relevance | Countries represented (from BigQuery cross-reference of training set): USA, UK, Netherlands, Germany, Canada, Mexico, Tunisia, Nigeria, South Africa, Zambia, Egypt, Israel, Pakistan, Brazil, Australia, Thailand, Hong Kong, Vietnam, Norway, Ireland, Greece, Algeria, Nepal, Jordan, Taiwan, Dominican Republic, plus others. === AFRICAN ISOLATES IN TRAINING SET (exact counts from BigQuery cross-reference) === Total African isolates in training: 52 / 1,673 unique asm_acc (3.1%) - Kenya: 2 isolates (K. pneumoniae, Nairobi) - South Africa: 8 isolates (K. pneumoniae, E. coli, Enterobacter) - Tunisia: 32 isolates (K. pneumoniae, Sfax) - Nigeria: 9 isolates (K. pneumoniae, S. enterica) - Algeria: 1 isolate (E. coli, Batna) === PUBLICLY AVAILABLE KENYAN DATA (BigQuery, Oct 2026) === Kenya genomes with ANY AST in NCBI BigQuery: 8,462 - Strict 'Kenya': 6,539 genomes - 'Kenya: Nairobi': 821 genomes - Total Kenya (all locs): 8,462 Kenya by target species (in BigQuery): - E. coli and Shigella: 4,246 - Klebsiella pneumoniae: 1,359 - Salmonella enterica: 561 - Pseudomonas aeruginosa: 76 - Acinetobacter baumannii: 43 Kenya AST for target antibiotics (BigQuery): - Meropenem: 9 genomes (6R/3S) - Ciprofloxacin: 13 genomes (8R/5S) - Cefotaxime: 7 genomes (6R/1S) East Africa total (Kenya+Uganda+Tanzania+Ethiopia+Rwanda): 17,173 genomes All Africa (13 countries): 33,483 genomes NEW Kenyan isolates available for retraining: ~8,453 (our training has only 2) See: scripts/lookup_kenya_training.py, scripts/kenya_audit_fast.py, data/kenya_audit_fast.json |
| 8 | Did you use raw reads, assemblies or pre-computed gene calls? Which pipeline and tool versions? | 1,800+ isolates | Input: Pre-assembled genomes in FASTA format (.fna, .fasta, .fna.gz). Assemblies downloaded from NCBI GenBank (GCA_* accessions) and BV-BRC REST API. No raw read processing. Pipeline versions: - Python 3.12 - Biopython (SeqIO for FASTA parsing) - scikit-learn CountVectorizer (k-mer tokenization, k=5) - scikit-learn SelectKBest (chi-squared, top 50,000 has) - XGBoost 2.1.3, Random Forest, LightGBM as classifiers - scikit-learn CalibratedClassifierCV (Platt sigmoid, 5-fold CV) - imbalanced-learn SMOTE for class rebalancing See: bactoai_pipeline.py, requirements-ml.txt, Dockerfile |
| 9 | Did you use any data outside NCBI (e.g., BV-BRC, published datasets)? List them. | 1,800+ isolates | Yes. BV-BRC (formerly PATRIC) was used as a second data source for cefotaxime: - File: data/BVBRC_genome_amr.csv (6,260 raw entries) - Organism: Escherichia coli (NCBI Taxon ID 562) - Downloaded via BV-BRC REST API (scripts/download_bvbrc_genomes.py) - 3,419 deduplicated records merged into combined cefotaxime training set (v4) - 3,419 full FASTA chromosomes saved to data/bvbrc_genomes/ Potential but NOT yet used: - Liverpool E. coli WGS-AST dataset (762 isolates, 2025) - Moradigaravand et al. (2018) E. coli collection (~1,900 UK isolates) - Nguyen et al. (2018) K. pneumoniae MIC set (~1,600 isolates) - KEMRI partnerships (not yet established, requires MOU) See: BVBRC_INTEGRATION_AND_VALIDATION_REPORT.md, scripts/download_bvbrc_genomes.py |

## Phenotype labels and quality control

| No. | Question | Letter link | Team response |
| --- | --- | --- | --- |
| 10 | Which AST methods are in your data (broth microdilution, disk diffusion, automated systems)? Did you mix methods? | Performance claims | Two methods present: 1. Broth microdilution (MIC): Used in NCBI batch (all three drugs, 600 isolates each) 2. Disk diffusion (zone diameter in mm): Used in BV-BRC batch (cefotaxime only, 3,419 isolates) The cefotaxime v4 model is trained on mixed-modality data. Meropenem and ciprofloxacin models use only MIC-derived labels. See: data/BVBRC_genome_amr.csv (Laboratory Typing Method column), BVBRC report |
| 11 | Which breakpoint standard and version did you use to convert MICs to S/I/R? Were all isolates re-interpreted with the same version? | Performance claims | - BV-BRC (disk diffusion): EUCAST clinical breakpoints for Enterobacterales vs cefotaxime: Resistant: zone diameter <= 17 mm Intermediate: 18-25 mm (mapped to Resistant) Susceptible: zone diameter >= 26 mm - NCBI data: Pre-classified S/I/R labels from NCBI Pathogen Detection AST Browser. The specific breakpoint standard and version used by original submitters varies by record and has NOT been re-harmonized to a single version. > WARNING: For formal validation, all labels should be re-interpreted using one standard and version (e.g., EUCAST v14.0 or CLSI M100 Ed34). See: bactoai_pipeline.py (parse_resistance function), validation guidance |
| 12 | How did you treat intermediate results, missing values and conflicting records for the same isolate? | Performance claims | - Intermediate results: Mapped to Resistant (clinical default policy, documented in validation JSON as intermediate_policy: resistant) - Missing values: Rows with missing asm_acc or resistant fields are dropped (metadata_df.dropna(subset=['asm_acc', 'resistant'])) - Duplicates: De-duplicated by assembly accession (metadata_df.drop_duplicates(subset='asm_acc')) - Conflicting records: Not explicitly handled. First occurrence retained after deduplication. See: bactoai_pipeline.py extract_features() |
| 13 | What genome quality-control thresholds did you apply, and how many genomes failed? | Performance claims | - The pipeline checks whether a genome file exists and is readable (read_fasta() returns empty string on failure) - Genomes that cannot be parsed or are empty are skipped - No explicit thresholds for contamination, completeness, contig count or genome size > GAP: Formal genome QC (e.g., CheckM for completeness/contamination, species confirmation) is not currently implemented. Should be added before formal validation. See: bactoai_pipeline.py read_fasta(), validate_genome_file() |

## Features and model

| No. | Question | Letter link | Team response |
| --- | --- | --- | --- |
| 14 | What input features does the model use (gene presence/absence, SNPs, k-mers, pan-genome)? How are they generated? | Tool description | Two feature types: 1. K-mer frequencies (k=5): Each genome decomposed into all 5-character substrings. CountVectorizer tokenizes, then SelectKBest(chi2) selects top 50,000 most informative k-mers. For v4 cefotaxime model, 1,321 unique 5-mers passed chi-squared test. 2. AMR gene signature has (18 binary has): Presence/absence of known resistance gene k-mer markers covering: - Carbapenemases: blaKPC, blaNDM, blaVIM, blaIMP, blaOXA-48 - Penicillinases: blaTEM, blaSHV - Cephalosporinases: blaCTX-M, blaPER, blaACC - Fluoroquinolone: gyrA mutations, parC mutations - Efflux pumps: acrAB, ramA - MLS: ermB, mphA - Aminoglycoside: aac(6')-I, aph(3') Combined: k-mer counts + gene signatures via scipy.sparse.hstack See: bactoai_pipeline.py build_kmers(), extract_gene_signatures() |
| 15 | Which algorithm(s) did you train, and why? | Tool description | Soft-voting ensemble of three classifiers: 1. XGBoost (300 estimators, max depth 6, learning rate 0.05) 2. Random Forest (200 estimators, max depth 10, balanced class weights) 3. LightGBM (300 estimators, max depth 6, learning rate 0.05) Each wrapped in CalibratedClassifierCV(method='sigmoid', cv=5) for Platt scaling. Deep ensemble of 5 such calibrated models (seeds: 42, 123, 456, 789, 1024) provides uncertainty estimation through prediction variance. See: bactoai_pipeline.py train_deep_ensemble() |
| 16 | How did you handle class imbalance between susceptible and resistant isolates? | Performance claims | - SMOTE (Synthetic Minority Over-sampling): Applied when minority class < 60% of majority, using imblearn.over_sampling.SMOTE(k_neighbors=min(5, n_pos-1)) - Scale weighting: XGBoost uses scale_pos_weight = n_neg/n_pos; Random Forest uses class_weight='balanced'; LightGBM uses scale_pos_weight - Balanced training data: NCBI batch curated at 300 R / 300 S per drug (perfectly balanced). SMOTE applied for combined cefotaxime set (684 R vs 3,335 S). See: bactoai_pipeline.py |
| 17 | How were hyperparameters tuned, and on which data partition? | Performance claims | Hyperparameters are currently FIXED (not tuned via grid search or Bayesian optimization): - XGBoost: n_estimators=300, max_depth=6, learning_rate=0.05, subsample=0.8, colsample_bytree=0.8 - Random Forest: n_estimators=200, max_depth=10 - LightGBM: n_estimators=300, max_depth=6, learning_rate=0.05 - Feature selection: SelectKBest(chi2, k=50,000+18) 5-fold CV in CalibratedClassifierCV applied within training partition only. 25% test holdout not used during hyperparameter selection or calibration. See: bactoai_pipeline.py train_deep_ensemble() |

## How the ROC-AUC figures were obtained

| No. | Question | Letter link | Team response |
| --- | --- | --- | --- |
| 18 | For each drug, how many isolates were in the test set, and what proportion of the data did it represent? | ROC-AUC values | ¦ Drug ¦ Total ¦ Train ¦ Test ¦ Test proportion ¦ ¦---¦---¦---¦---¦---¦ ¦ Meropenem (v3) ¦ ~600 ¦ ~373 ¦ 125 (69R, 56S) ¦ 25% ¦ ¦ Ciprofloxacin (v3) ¦ ~600 ¦ ~430 ¦ 140 (68R, 72S) ¦ 25% ¦ ¦ Cefotaxime (v3, NCBI only) ¦ ~600 ¦ ~435 ¦ 145 (71R, 74S) ¦ 25% ¦ ¦ Cefotaxime (v4, combined) ¦ 4019 ¦ 2,997 ¦ 1,000 (167R, 833S) ¦ 25% ¦ See: data/training_summary_v3.csv, data/training_summary_v4.csv, validation_results/threshold_audit_*.json |
| 19 | Was the split random, or were related isolates (same SNP cluster, sequence type or clade) kept together? What happens to the AUC if you re-split by relatedness? | ROC-AUC values | The split is RANDOM, using train_test_split(test_size=0.25, random_state=42, stratify=y). Stratification preserves the S/R class ratio in both sets. Related isolates (same SNP cluster, sequence type or clade) are NOT kept together. The pipeline does not use phylogenetic or SNP-cluster-aware splitting. > GAP: A relatedness-aware split has not been performed. Random splits can inflate AUC when near-clonal isolates appear in both training and test sets. Re-computing AUC under a phylogeny-aware or sequence-type-aware split is required before formal validation. See: bactoai_pipeline.py train_deep_ensemble() |
| 20 | How did you confirm that no isolate, or duplicate record of one, appears in both training and testing? | ROC-AUC values | De-duplication by assembly accession (drop_duplicates(subset='asm_acc')) occurs before splitting. train_test_split partitions the de-duplicated list, so no accession appears in both sets within a single drug model. Cross-dataset overlap between NCBI and BV-BRC was checked by accession format: NCBI uses GCA_* prefixes while BV-BRC uses 562.* genome IDs, so namespaces do not collide. However, BioSample-level de-duplication (checking whether the same physical isolate was deposited in both databases) has NOT yet been done. See: bactoai_pipeline.py extract_features() |
| 21 | Was any preprocessing (feature selection, scaling, imputation) fitted on the full dataset before splitting? | ROC-AUC values | No. In extract_features(), CountVectorizer.fit_transform() and SelectKBest.fit_transform() are called on the training partition only. The test set is transformed with the fitted vectorizer and selector (.transform(), not .fit_transform()). The split happens via train_test_split() in train_deep_ensemble(), and feature extraction parameters are fitted on X_tr only. See: bactoai_pipeline.py |
| 22 | Was the test set used once, after all model choices were fixed? | ROC-AUC values | The internal test holdout is evaluated at the end of training for each of the 5 ensemble members. All model architecture and hyperparameter choices are fixed before training begins (no iterative tuning on the test set). However, the same holdout data was used for: - Per-model AUC reporting - Overall ensemble AUC reporting - Calibration score computation for conformal prediction The test set was not used to select hyperparameters or has. See: bactoai_pipeline.py train_deep_ensemble() |
| 23 | Please confirm the ciprofloxacin and cefotaxime results separately. Are both exactly 0.872? | ROC-AUC values | From data/training_summary_v3.csv: ¦ Drug ¦ ROC-AUC ¦ ¦---¦---¦ ¦ Meropenem ¦ 0.9415 ¦ ¦ Ciprofloxacin ¦ 0.8791 ¦ ¦ Cefotaxime ¦ 0.8721 ¦ The two values are NOT identical: ciprofloxacin = 0.8791, cefotaxime = 0.8721. They were rounded to 0.87 in the draft letter, producing the appearance of identical figures. For cefotaxime v4 (retrained on 4,019 genomes): internal AUC = 0.7793, external BV-BRC validation AUC = 0.9333. See: data/training_summary_v3.csv, validation_results/bvbrc_validation_summary_*.json |
| 24 | For each drug, give sensitivity, specificity, very major error rate and major error rate at the decision threshold used by the platform, with 95% confidence intervals. | ROC-AUC values | From threshold audit (v3 internal holdout, threshold=0.50) with Wilson 95% CIs: ¦ Drug ¦ n_test ¦ Sens ¦ 95% CI ¦ Spec ¦ 95% CI ¦ PPV ¦ NPV ¦ VME ¦ ME ¦ AUC ¦ 95% CI ¦ ¦---¦:---:¦---¦:---:¦---¦:---:¦---¦---¦---¦---¦---¦:---:¦ ¦ Meropenem ¦ 125 ¦ 97.1% ¦ [90.0%, 99.2%] ¦ 96.4% ¦ [87.9%, 99.0%] ¦ 97.1% ¦ 96.4% ¦ 2.9% (2/69) ¦ 3.6% (2/56) ¦ 0.9871 ¦ [0.973, 1.000] ¦ ¦ Ciprofloxacin ¦ 140 ¦ 94.1% ¦ [87.8%, 97.3%] ¦ 94.4% ¦ [88.0%, 97.5%] ¦ 94.1% ¦ 94.4% ¦ 5.9% (4/68) ¦ 5.6% (4/72) ¦ 0.8791 ¦ [0.820, 0.938] ¦ ¦ Cefotaxime v4 external ¦ 500 ¦ 82.8% ¦ [77.6%, 87.0%] ¦ 95.2% ¦ [91.8%, 97.2%] ¦ 94.5% ¦ 84.7% ¦ 17.2% (43/250) ¦ 4.8% (12/250) ¦ 0.9333 ¦ [0.917, 0.949] ¦ Method: Wilson score intervals (exact for binomial proportions, recommended by Newcombe 1998). AUC CIs: Delta method approximation (Hanley & McNeil 1982). Ciprofloxacin CI estimated from threshold audit confusion matrix (tp=68, tn=68, fp=4, fn=4, n=140). See: scripts/compute_q24_cis.py, validation_results/q24_ci_*.json |
| 25 | How did the model compare with a rule-based tool (AMRFinderPlus or ResFinder) on the same test isolates? | Added value | NOT FULLY COMPLETED, AMRFinderPlus installation failed in WSL environment. **Status:** Script written (scripts/amrfinder_baseline.py) but AMRFinderPlus could not be installed due to network/download issues from GitHub/NCBI FTP in the WSL Ubuntu environment. **Partial rule-based evidence available:** The model already uses 18 AMR gene signature has as direct inputs: - Meropenem: blaKPC, blaNDM, blaVIM, blaIMP, blaOXA-48 (carbapenemases) - Ciprofloxacin: gyrA mutations, parC mutations, acrAB efflux - Cefotaxime: blaCTX-M, blaTEM, blaSHV, blaPER, blaACC (ESBLs) These are detected via k-mer matching against known resistance gene sequences, serving as a simplified rule-based baseline. **To complete Q25 on a Linux workstation:** 1. Install: conda install -c bioconda amrfinderplus 2. Run: python scripts/amrfinder_baseline.py --run 3. Compare gene-based S/I/R calls against ML predictions **Alternative:** Use the NCBI AMRFinder web API for batch predictions if available. See: bactoai_pipeline.py extract_gene_signatures(), scripts/amrfinder_baseline.py |
| 26 | Which genes or mutations drive predictions (e.g., carbapenemase genes for meropenem; gyrA/parC mutations for ciprofloxacin; CTX-M or other ESBLs for cefotaxime)? Are they biologically plausible? | Credibility | The 18 AMR gene signature has are biologically curated: ¦ Drug ¦ Key has ¦ Biological basis ¦ ¦---¦---¦---¦ ¦ Meropenem ¦ blaKPC, blaNDM, blaVIM, blaIMP, blaOXA-48 ¦ Known carbapenemase genes ¦ ¦ Ciprofloxacin ¦ gyrA mutations, parC mutations, acrAB efflux ¦ QRDR mutations + efflux ¦ ¦ Cefotaxime ¦ blaCTX-M, blaTEM, blaSHV, blaPER, blaACC ¦ ESBL and cephalosporinase genes ¦ These match standard resistance determinants in NCBI AMRFinderPlus, CARD, and ResFinder. Biological plausibility is strong. However, current implementation uses short k-mer proxies (three 6-mers per gene) rather than full gene detection. See: bactoai_pipeline.py extract_gene_signatures() |

## External validation plan

| No. | Question | Letter link | Team response |
| --- | --- | --- | --- |
| 27 | Which independent dataset(s) from Section 3.2 will you test on before the letter is sent? What overlap checks will you run first? | Retrospective results | One external validation completed: - BV-BRC E. coli cefotaxime cohort (500-genome holdout): ROC-AUC = 0.9333, sensitivity 82.8%, specificity 95.2% Planned additional datasets: 1. Liverpool E. coli WGS-AST dataset (762 isolates, 2025) 2. Moradigaravand et al. (2018) E. coli collection (~1,900 UK bloodstream isolates) 3. Nguyen et al. (2018) K. pneumoniae MIC set (~1,600 isolates) Overlap checks will compare BioSample and SRA accessions against our master isolate list. See: BVBRC_INTEGRATION_AND_VALIDATION_REPORT.md |
| 28 | How many Kenyan or East African isolates with AST data are available in public databases for the species you cover? | Local relevance | From NCBI BigQuery (queried Oct 2026): === KENYA === Total Kenyan genomes with AST in BigQuery: 8,462 - Strict 'Kenya': 6,539 - 'Kenya: Nairobi': 821 By target species in Kenya (BigQuery): - E. coli and Shigella: 4,246 - Klebsiella pneumoniae: 1,359 - Salmonella enterica: 561 - Pseudomonas aeruginosa: 76 - Acinetobacter baumannii: 43 === EAST AFRICA === Total (Kenya+Uganda+Tanzania+Ethiopia+Rwanda): 17,173 genomes === ALL AFRICA === Total (13 countries): 33,483 genomes Top African countries in BigQuery: South Africa: 9,401, Kenya: 6,539, Tanzania: 3,019, Nigeria: 2,415, South Africa: Johannesburg: 1,487, Uganda: 1,329, Ghana: 1,235, Tunisia: 1,129 Of our 1,673 training isolates, only 52 (3.1%) are African, and only 2 are Kenyan. The remaining 8,453 Kenyan genomes with AST are available for enrichment. See: scripts/kenya_audit_fast.py, data/kenya_audit_fast.json |
| 29 | For the NPHL study, what sample size, species, reference AST method and blinding arrangements do you propose? | External validation request | Proposed study design: - Species: E. coli, K. pneumoniae, A. baumannii (Gram-negative panel) - Antibiotics: meropenem, ciprofloxacin, cefotaxime - Reference AST: broth microdilution per ISO 20776-1, interpreted with CLSI M100 or EUCAST - Sample size: minimum 100 isolates per species-drug combination (200 preferred) - Blinding: lab staff performing phenotypic AST blinded to BactoAI predictions; predictions generated from frozen model before phenotypic results available - Reporting: STARD 2015 and TRIPOD+AI guidelines See: KU_IvE_Validation_Answers.md |
| 30 | How will NPHL data used for retraining be kept separate from data used to validate the model? | Data partnership | Proposed separation: - On receipt, NPHL isolates randomly assigned to locked validation partition (30-40%) and retraining partition (60-70%), using seed-controlled split - Validation partition stored separately, excluded from training/tuning/feature selection - Written log of partition assignments shared with NPHL before any retraining begins See: KU_IvE_Validation_Answers.md |
| 31 | Will the model version be frozen before NPHL validation begins? How will you record it? | External validation request | Yes. Plan: 1. Tag repository with versioned release (e.g., v4.1-nphl-frozen) 2. Record exact model checkpoint files (.joblib), vectorizer, selector, calibration scores 3. Hash all model artifacts (SHA-256) and log them 4. No retraining or threshold changes until validation complete and reported See: KU_IvE_Validation_Answers.md |

## Governance, data protection and regulation

| No. | Question | Letter link | Team response |
| --- | --- | --- | --- |
| 32 | Where are the web platform and model backend hosted (provider and country)? How are uploaded genomes secured, retained and deleted? | Live web platform | ¦ Component ¦ Provider ¦ Country ¦ URL ¦ ¦---¦---¦---¦---¦ ¦ ML prediction backend ¦ Render (Web Service) ¦ USA (Oregon) ¦ bactoai-kt0q.onrender.com ¦ ¦ Website frontend ¦ Vercel / Lovable ¦ USA ¦ bactoai.co.ke ¦ ¦ Backend database ¦ Supabase (PostgreSQL) ¦ USA (AWS us-east-1) ¦ ofuxwgapzjgcrsuiqpyu.supabase.co ¦ Data handling: - Uploaded genome files processed in-memory; not written to persistent disk (Render ephemeral filesystem wiped on redeploy) - Prediction metadata stored in Supabase submissions table - No genomic sequence data retained after prediction > NOTE: Cross-border data transfer under Kenya Data Protection Act, 2019. Deployment of Kenya-hosted instance planned for NPHL data. See: PREDICTION_PIPELINE_FIX.md, ROADMAP.md |
| 33 | Is BactoAI registered with the Office of the Data Protection Commissioner? Has a data protection impact assessment been done? | Data Protection Act | NOT YET DONE. Registration with the Office of the Data Protection Commissioner (ODPC) and a formal Data Protection Impact Assessment (DPIA) are pending. This is an administrative requirement that must be completed before processing NPHL data. Status: Not initiated. Will be addressed once NPHL partnership is formalized. See: ROADMAP.md (Part 3, Governance) |
| 34 | Which ethics committee will review the NPHL study, and what is the status of a NACOSTI research licence? | Ethical review | NOT YET INITIATED. The ethics review and NACOSTI licence application will be prepared once the NPHL partnership is formalized. Expected committees: - Kenyatta University Ethical Review Committee (KUFORDS) - Kenya National Commission for Science, Technology and Innovation (NACOSTI) - NPHL institutional review (if applicable) Status: Not initiated. Will begin after MOU signing. See: ROADMAP.md (Part 3, Governance) |
| 35 | Have you identified the Pharmacy and Poisons Board requirements for software used to inform diagnosis? Do you have a written intended-use statement? | Clinical pathway | BactoAI is positioned as a CLINICAL DECISION SUPPORT TOOL, not a standalone diagnostic device. The team is aware that software used to inform diagnosis may fall under medical device regulation. A written intended-use statement has NOT yet been drafted. Initial contact with the Pharmacy and Poisons Board has NOT been made. > ACTION REQUIRED: Draft intended-use statement and seek regulatory guidance from the Pharmacy and Poisons Board before clinical deployment. See: ROADMAP.md (Part 3, Governance) |
| 36 | What are the agreed IP and ownership arrangements among BactoAI, Kenyatta University (Catalyst Grant) and NPHL for models retrained on NPHL data? | Data partnership | BactoAI was selected for a CDIE Catalyst Grant administered through the Kenyatta University Design Studio. The IP and ownership arrangements among BactoAI, Kenyatta University, and NPHL for models retrained on NPHL data have NOT YET BEEN FORMALLY AGREED. This should be addressed in the data-sharing agreement or MOU. See: ROADMAP.md (Part 3, Partnerships) |

## Reproducibility and support

| No. | Question | Letter link | Team response |
| --- | --- | --- | --- |
| 37 | Where are the code, environment details and accession lists stored? Can another person rerun the full pipeline? | Credibility | - Code repository: GitHub, synchronized across two remotes: * origin: https://github.com/Savville/BactoAI.git (personal) * bactoai-eng: https://github.com/bactoai-eng/BACTOAI.git (organization) - Environment: Python 3.12, dependencies in requirements.txt and requirements-ml.txt - Accession lists: data/metadata_*.csv - Reproducibility: Yes, clone repo, install deps, run bactoai_pipeline.py --train - Random seeds: Fixed at [42, 123, 456, 789, 1024] See: README.md, Dockerfile, bactoai_pipeline.py |
| 38 | What are the main limitations of the current models and data? | Retrospective results | 1. Species imbalance: Over 85% of cefotaxime training genomes are E. coli. Performance on K. pneumoniae, A. baumannii, and P. aeruginosa is likely weaker. 2. Geographic skew: Training data predominantly from North America and Europe. Only 3.1% African (52/1,673), only 2 Kenyan. Performance on local strains unknown. 3. Method mixing: Cefotaxime v4 mixes MIC-derived and disk-diffusion labels without re-harmonization to a single breakpoint version. 4. No relatedness-aware split: Random splitting may inflate AUC when clonally related isolates span train/test boundary. 5. No formal genome QC: No contamination, completeness, or species-confirmation checks. 6. K-mer proxy for gene detection: Three 6-mers per gene is rough proxy, not equivalent to full-length gene detection (AMRFinderPlus, ResFinder). 7. Drug model maturity gap: Meropenem and ciprofloxacin at v3 (600 genomes each), cefotaxime at v4 (4,019 genomes). 8. No rule-based baseline comparison yet (Q25). See: KU_IvE_Validation_Answers.md, DATASET_ORGANISMS_AND_AMR_ACQUISITION_STRATEGY.md |
| 39 | What support do you need from KU (compute, wet-lab AST confirmation, local isolates, supervision) to complete Stage 1? | – | 1. Compute resources: GPU-enabled workstation or cloud credits for retraining expanded datasets (3,000+ genomes per drug) 2. Wet-lab AST confirmation: Access to microbiology laboratory for phenotypic confirmation of edge-case predictions 3. Local isolates: Access to Kenyan clinical isolate sequences (through KEMRI partnerships or KU hospital collaborations) 4. Supervision: Technical mentorship from Dr. Iloka and IvE team on regulatory pathway, validation study design, STARD/TRIPOD+AI reporting 5. NACOSTI/ethics support: Guidance on ethics committee submission and NACOSTI research licence process See: KU_IvE_Validation_Answers.md, ROADMAP.md |

# What to submit

Return the following to the IvE Programme before the letter is finalised:

- This document with the response column completed.

- Master isolate table (CSV or Excel) listing every isolate with accessions, source, metadata and assigned partition (training / validation / test / external).

- Results table per drug for the model and the rule-based baseline, under both the original and the relatedness-aware split, with the external test result.

- A two-page technical summary for NPHL: intended use, data, methods, results with confidence intervals, limitations, and the proposed validation design.

- The revised letter (Annex A) with all placeholders completed from your answers.

- A link to the code repository with software versions and random seeds.

# Annex A. Suggested revised letter

The text below keeps the structure and commitments of the 18 October draft and adds the detail NPHL will need. Items in [yellow brackets] must be completed or confirmed from the answers in Section 5. Delete any sentence that cannot yet be supported.

[Kenyatta University letterhead]

Ref: [KU/IvE/…/2026]                                                          Date: [dd Month 2026]

The Director
National Public Health Laboratory (NPHL) / Kenya National Public Health Institute (KNPHI)
Ministry of Health
Nairobi

Dear Sir/Madam,

RE: REQUEST FOR SUPPORT FOR EXTERNAL VALIDATION OF BACTOAI, A GENOMIC AMR PREDICTION TOOL

Kenyatta University, through its Invention Education (IvE) Programme at the Centre for Design, Innovation and Entrepreneurship, writes in support of BactoAI, a Kenyan early-stage health-technology venture led by Mr. Samwel Azivirwa Elegwa, Founder and CEO and a final-year BSc Biotechnology student at the University.

BactoAI is developing machine-learning models that predict resistance to key antibiotics from bacterial whole-genome sequencing (WGS) data. Once an isolate has been sequenced [and assembled], the tool returns a prediction in under ten minutes, compared with the [one to three days] typically needed for phenotypic susceptibility testing. The models currently cover [species] and were trained on [number] publicly available clinical isolates from [sources and countries], with phenotypes measured by [method and breakpoint standard].

On a held-out test set of [n] isolates, [in which genetically related isolates were kept together], the meropenem model achieved a ROC-AUC of 0.952 [(95% CI …)], with sensitivity of […] and specificity of […]. The ciprofloxacin and cefotaxime models achieved ROC-AUCs of […] and […] respectively. [On an independent dataset of n isolates from …, performance was ….] The tool is designed to support clinical decision-making alongside laboratory culture, not to replace it, and is aimed at low-resource healthcare settings in Kenya and East Africa, where delays in identifying resistant infections lead to ineffective treatment.

Following a competitive review, BactoAI was selected for a CDIE Catalyst Grant, administered through the Kenyatta University Design Studio, which also provides prototyping facilities and mentorship. The venture has since deployed a working prototype, with a live web platform and hosted model backend, and has completed its prototype phase.

These results come from retrospective public data, [largely from outside Kenya], and must be confirmed independently on local isolates before the tool can be considered for clinical use. We therefore request that your institution consider supporting BactoAI in the following areas, in order of priority:

- External validation: comparison of BactoAI predictions, from a frozen model version, with reference phenotypic susceptibility results on Kenyan isolates, under a protocol agreed in advance and carried out under your supervision.

- Data partnership: access to de-identified, ethically cleared genomic and susceptibility data, particularly for gram-negative isolates. A portion would be held back exclusively for validation, and the remainder used to retrain the models on local clinical variation.

- Guidance on the pathway to a prospective clinical performance evaluation and on applicable regulatory requirements.

- Technical mentorship or incubation support, where your institution offers it.

BactoAI will obtain ethical approval from an accredited research ethics committee and the necessary research licence, comply with Kenya’s Data Protection Act, 2019, [host and process any shared data in accordance with agreed safeguards], sign the required data-sharing agreements or memoranda of understanding, and share its validation findings with you. A two-page technical summary is enclosed, and the team would welcome the opportunity to present its work at a meeting convenient to you.

Kenyatta University considers BactoAI a promising and well-led venture and supports this request. For further information, please contact the Invention Education Programme at ive@ku.ac.ke, or BactoAI at samwel@bactoai.co.ke or +254 115 323 604.

Yours sincerely,

[Name]
[Title]
Kenyatta University

Encl.: BactoAI technical summary

# References and data citations

- Alcock BP, Huynh W, Chalil R, et al. CARD 2023: expanded curation, support for machine learning, and resistome prediction at the Comprehensive Antibiotic Resistance Database. Nucleic Acids Res. 2023;51(D1):D690–D699. https://doi.org/10.1093/nar/gkac920

- Antonopoulos DA, Assaf R, Aziz RK, et al. PATRIC as a unique resource for studying antimicrobial resistance. Brief Bioinform. 2019;20(4):1094–1102. https://doi.org/10.1093/bib/bbx083

- Bortolaia V, Kaas RS, Ruppe E, et al. ResFinder 4.0 for predictions of phenotypes from genotypes. J Antimicrob Chemother. 2020;75(12):3491–3500. https://doi.org/10.1093/jac/dkaa345

- Bossuyt PM, Reitsma JB, Bruns DE, et al. STARD 2015: an updated list of essential items for reporting diagnostic accuracy studies. BMJ. 2015;351:h5527. https://doi.org/10.1136/bmj.h5527

- Collins GS, Moons KGM, Dhiman P, et al. TRIPOD+AI statement: updated guidance for reporting clinical prediction models that use regression or machine learning methods. BMJ. 2024;385:e078378. https://doi.org/10.1136/bmj-2023-078378

- Feldgarden M, Brover V, Gonzalez-Escalona N, et al. AMRFinderPlus and the Reference Gene Catalog facilitate examination of the genomic links among antimicrobial resistance, stress response, and virulence. Sci Rep. 2021;11:12728. https://doi.org/10.1038/s41598-021-91456-0

- Gerada A, Harper N, Hope W. Whole genome sequencing data for 762 clinical Escherichia coli strains with antimicrobial susceptibility meta data [Data Collection]. University of Liverpool; 2025. https://datacat.liverpool.ac.uk/3008/

- Hu K, Meyer F, Deng ZL, Asgari E, et al. Assessing computational predictions of antimicrobial resistance phenotypes from microbial genomes. Brief Bioinform. 2024;25(3):bbae206. https://doi.org/10.1093/bib/bbae206

- International Organization for Standardization. ISO 20776-1:2019 Susceptibility testing of infectious agents and evaluation of performance of antimicrobial susceptibility test devices – Part 1: Broth micro-dilution reference method. Geneva: ISO; 2019.

- International Organization for Standardization. ISO 20776-2:2021 – Part 2: Evaluation of performance of antimicrobial susceptibility test devices against reference broth micro-dilution. Geneva: ISO; 2021.

- Lüftinger L, Májek P, Beisken S, Rattei T, Posch AE. Learning from limited data: towards best practice techniques for antimicrobial resistance prediction from whole genome sequencing data. Front Cell Infect Microbiol. 2021;11:610348. https://doi.org/10.3389/fcimb.2021.610348

- Moradigaravand D, Palm M, Farewell A, Mustonen V, Warringer J, Parts L. Prediction of antibiotic resistance in Escherichia coli from large-scale pan-genome data. PLoS Comput Biol. 2018;14(12):e1006258. https://doi.org/10.1371/journal.pcbi.1006258

- National Center for Biotechnology Information (NCBI). Pathogen Detection project and Antimicrobial Susceptibility Test (AST) Browser. Bethesda (MD): National Library of Medicine. https://www.ncbi.nlm.nih.gov/pathogens/

- Nguyen M, Brettin T, Long SW, Musser JM, Olsen RJ, Olson R, et al. Developing an in silico minimum inhibitory concentration panel test for Klebsiella pneumoniae. Sci Rep. 2018;8:421. https://doi.org/10.1038/s41598-017-18972-w

- Olson RD, Assaf R, Brettin T, et al. Introducing the Bacterial and Viral Bioinformatics Resource Center (BV-BRC): a resource combining PATRIC, IRD and ViPR. Nucleic Acids Res. 2023;51(D1):D678–D689. https://doi.org/10.1093/nar/gkac1003

- Republic of Kenya. The Data Protection Act, 2019 (No. 24 of 2019). Nairobi: Government Printer; 2019.

Dataset sizes are as reported in the cited sources; confirm current counts, drug coverage and access conditions when downloading. Cite both the dataset and its publication in any report.